## HSE action plan
OBJECTIVES | Responsible | Timing at OT |  | Timings in UB
|  | Start Date | End Date | Start Date | End Date
SAFETY AWARENESS PROGRAM
HazID & Risk Management training | G, Safety team and TMTI |  |  | 2014-02-20 | Scheduled
Company Safety Induction (based on SMS Safety Orientation program) |  |  |  | 2014-04-10 | Scheduled
Job Hazard Analysis training |  |  |  | 2014-04-10 | Scheduled
Take 5 training |  |  |  | 2014-04-10 | Scheduled
Workplace Inspection Training |  |  |  | 2014-04-10 | Scheduled
Incident investigation training |  |  |  | 2014-02-20 | Scheduled
Incident reporting training
- Develop presentation |  |  |  | 2014-02-03 | 2014-02-08
- Review and approve by Directors |  |  |  | 2014-02-09 | 2014-02-14
- Schedule the training and approve by Managers |  |  |  | 2014-02-15 | 2014-02-18
- Make practical training |  |  |  | 2014-02-20 | Every month
- Sign off sheets to be scanned to P drive and attendance will be marked at Training matrix |  |  |  | After training | After training
LEADERSHIP PROGRAM
Visible leadership by example | G
- Provide OHSE leadership training for supervisors and OHSE staffs |  |  |  | 2014-02-20 | Every month
- Set KPI for supervisors and OHSE staffs |  |  |  | 2014-03-01 | 2014-03-09
- KPI shall be reviewed and approved by Directors |  |  |  | 2014-03-10 | 2014-03-19
- Inform to all supervisors about KPI |  |  |  | 2014-03-20 | 2014-04-01
- Measure performances of supervisors against KPI |  |  |  | Before annual KPI review
- Develop leadership matrix as poster |  |  |  | 2014-04-05 | 2014-04-10
COMMUNICATION
Pre-start meeting - Improve quality | G, Tsogtbayar, Nanjidsuren and Bat-Ireedui
- Random employees will run the pre-start safety talks |  |  |  | Daily | Daily
- Mentor employees how to run pre-start meeting the day before for 30min |  |  |  | Daily | Daily
- Provide usefull materials which will be used at Pre-start talk |  |  |  | Daily | Daily
- More practical examples will be discussed at Pre-start talk |  |  |  | Daily | Daily
Weekly meeting - Support the meeting
- Improve communication between departments |  |  |  | Weekly | Weekly
- Improve initiatives of weekly meeting members |  |  |  | Weekly | Weekly
JOSHC meeting - Utilize the meeting
- Improve member's knowledge |  |  |  | Monthly | Monthly
- Utilize the meeting |  |  |  | Monthly | Monthly
- OHSE Manager shows leadership at the meeting and arranges it properly |  |  |  | Monthly | Monthly
HAZID AND RISK REDUCTION PROGRAM
Take 5 book | G and Tsogtbayar
- Develop book |  |  |  | 2014-01-01 | Completed
- Review and approve by Directors |  |  |  | 2014-01-30 | Completed
- Get published |  |  |  | 2014-02-10 | 2014-03-07
- Prepare to give the books to employees after Take 5 training |  |  |  | 2014-03-09 | 2014-04-01
Job Hazard Analysis template
- Develop the template |  |  |  | 2014-02-01 | 2014-02-10
- Review and approve by Directors |  |  |  | 2014-02-11 | 2014-02-28
- Print out |  |  |  | 2014-03-05 | 2014-03-06
- Be handy for employees |  |  |  | 2014-03-07 | 2014-03-10
Workplace Inspection template
- Develop |  |  |  | 2014-01-30 | 2014-02-05
- Review and approve by Directors |  |  |  | 2014-02-11 | 2014-02-28
- Print out |  |  |  | 2014-03-05 | 2014-03-06
- Be handy for employees |  |  |  | 2014-03-07 | 2014-03-10
Hazard report sheet
- Develop Hazard report sheet |  |  |  | 2014-02-05 | 2014-02-06
- Review and approve by Directors |  |  |  | 2014-02-07 | 2014-02-12
- Get published within Take 5 book |  |  |  | 2014-02-10 | 2014-03-07
- Prepare to give the books to employees after HazID & Risk Management training |  |  |  | 2014-03-09 | 2014-04-01
Remedial Action Tracking System
- Develop RATS system |  |  |  | 2014-01-01 | Completed
- Review and approve by Directors |  |  |  | 2014-01-10 | Completed
- Run the system for chasing up corrective actions raised from WPI, Incident Reports, Reported Hazards and JHA |  |  |  | 2014-01-20 | Completed
REDUCE ALCOHOL & DRUGS AT WORKPLACE
Educate the employees | Committee against Alcohol Control by: Safety team |  |  | 2/30/2014 | 2/30/2014
- Prepare presentation for educational program and small presentation for toolbox talk |  |  |  | 2/30/2014 | 2/30/2014
- Present the educational materials and generate discussion about Danger of Alcohol |  |  |  | 2/30/2014 | 2/30/2014
- Enforce workplace control on Breath test |  |  |  | For a year
APPROVED JOHSC COMMITTEE
We have JOHS Committee which meets with resolution #126 of Labor ministry | Borgil |  |  | 2014-03-01 | 2014-03-05
Organizing the Committee meetings and feedbacks |  |  |  | For a year
Chase up the corrective actions and drive to effective results |  |  |  | For a year
ELECTRONIC MSDS SOFTWARE
Search competitive software MSDS (Chemwatch) that meet with our operation | G, JC and Larry Advise with all directors and managers |  |  | Completed | Completed
Get approval from Directors |  |  |  | Completed | Completed
Be trained to use the softwares and establish properly |  |  |  | Completed | Completed
HSE POLICIES AND PROCEDURES TO DEVELOP
TM UB facilities Emergency Response Plan | Bat-Ireedui |  |  | 2014-03-01 | 2014-04-01
OHSE EMPLOYEE DEVELOPMENT
Arrange Safety Coordinators skill development training | G, JC, Larry, Brett, Stephen and Amanda |  |  | 2014-01-01 | 2014-01-30
Train OHSE staffs for professional trainings to improve their skill:
- Cert IV course for Safety coordinators by ITC LLC |  |  |  | 2014-03-01 | 2014-03-15
- Safety officer and Committee member training by OSHMI |  |  |  | 2014-02-01 | 2014-05-01
WORKPLACE EVALUATION BY HEALTH CENTER
TM workplaces will be evaluated by Health center | Nanjidsuren |  |  | 2014-10-01 | 2014-10-15
SAFETY INTERNAL AUDIT SYSTEM
Research of SMS safety audit system (COR) to determine suitibilty to TM | Tsogtbayar |  |  | 2014-11-01 | 2014-11-10
Research Mongolian Government safety audit requirements for suitibilty to TM |  |  |  | 2014-11-10 | 2014-11-20
Develop first draft of TM internal audit system for review by Directors |  |  |  | 2014-11-20 | 2014-11-30
Compile the internal audit against SMS and Mongolian audit requirements and report |  |  |  | 2014-12-05 | 2014-12-25
KPI in 2014 per 200.000 exposure hours
Lost Time Injury = 0
Total Recordable Injury Frequency < 0.73
Severity Rate < 1.94

## SMS Safety Orientation
OBJECTIVES | Responsible | Comment | Timings
|  |  | Start Date | End Date
Present what SMS has to TMTI trainers | Implementation by: OHSE team and TMTI Approved by: JC & Larry |  | Starting from 2-Apr-2014 for a year Every month Please, see Employees Development Plan
Plan resources, schedule and implementation with TMTI
Review SMS orientation program and improve if necessary, ie add Mongolian laws
- Employee orientation checklist
- SMS Orientation
- HSE1.01 - Health, Safety and Environment
- HSE1.02 - Incident Reporting
- HSE1.03 - Incident Investigation
- HSE1.04 - Hazard Assessment
- HSE1.05 - Field Level Risk Assessment
- HSE1.06 - Alcohol & Drug Policy
- HSE1.07 - Personal Protective Equipment
- HSE1.08 - Safety Meetings
- HSE1.09 - Safety Inspection and Audits
- HSE1.10 - Working Alone
- HSE1.11 - Vehicle Use
- HSE1.12 - Safety Legislation
- HSE1.13 - Illness and Injury Management
- HSE1.14 - Emergency Preparedness
- HSE1.15 - Records and Statistics
- PWR PT Contractor Questionaire
- New Employee Orientation Test Answer Sheet
- New Employee Orientation Test
Get approval from Directors on what we have add into SMS presentations
Transfer the approved presentations into Transwest template
Train the trainers at TMTI
Deliver to visitor below related inductions when they visit to our premises:
- Head office visitor induction
- UBSS visitor induction
- Warehouse visitor induction
- TMTI visitor induction