## HSE action plan
2015 OHSE PLAN
| OBJECTIVES | Responsible | Timing
|  |  | Start Date | End Date
CONTINUE SAFETY AWARENESS PROGRAM
| HazID & Risk Management training | OHSE team | 2015-04-10 | Done
| Company Safety Induction (based on SMS Safety Orientation program) |  | 2015-04-11 | Ongoing
| Job Hazard Analysis training |  | 2015-04-12 | Done
| Workplace Inspection Training |  | 2015-04-13 | Done
| Incident investigation training |  | 2015-02-20 | Ongoing
INTRODUCE SAFETY METRICS SYSTEM
| - Prepare the template | OHSE team | 2015-06-15 | Done
| - Set KPI after discussion with Heads of Departments and Directors |  | 2015-07-01 | Done
| - Train all employees based in UB |  | 2015-07-15 | Done
| - Complete Corporate Report |  | 2015-08-15 | Done
ENHANCE TO IMPROVE COMMUNICATION
| Pre-start meeting - Improve quality | OHSE team
| - Random employees will run the pre-start safety talks |  | Daily | Daily
| - Mentor employees how to run pre-start meeting the day before for 30min |  | Daily | Daily
| - Provide usefull materials which will be used at Pre-start talk |  | Daily | Daily
| - More practical examples will be discussed at Pre-start talk |  | Daily | Daily
| Weekly meeting - Support the meeting |  | Weekly | Weekly
| JOSHC meeting - Utilize the meeting |  | Bimonthly | Bimonthly
HARMONIZE HAZID AND RISK REDUCTION PROGRAM
| Remedial Action Tracking System | All Departments
| - Run the system for chasing up corrective actions raised from WPI, Incident Reports, Reported Hazards and JHA |  | Weekly | Completed
MAKE ZERO ALCOHOL AT WORKPLACE
| - Enforce workplace control on Breath test | All personnel | Ongoing, YTD - Zero Incident
COMPLETE MSDS AT WORKPLACE
| Complete the gap analysis and report | OHSE team | 2015-08-01 | Done
| Generate missing MSDSs |  | 2015-08-15 | Ongoing
| Train employees as per relevant MSDSs |  | 2015-10-01 | 2015-10-15
ENGAGE CONTRACTOR MANAGEMENT SYSTEM
| Induct all contractors as per TM policy and procedures | G | 2015-09-01 | 2015-09-30
| Add HSE clauses to all contracts between TM and contractor | G | 2015-09-07 | 2015-09-15
QUALIFY WITH AUDITS
| Qualify with OT annual HSE audit | G & Tsog | 2015-06-01 | Done
| Qualify with Sumitomo audit | G & Tsog
| Complete the internal audit as per SMS checklist | G & Tsog | 2015-12-01 | 2015-12-15
OHSE EMPLOYEE DEVELOPMENT
| Train OHSE staffs for professional trainings to improve their skill: | G
| - Cert IV course for Safety coordinators by ITC LLC |  | 2014-03-01 | Done
| - Safety officer and Committee member training by OSHMI |  | 2014-02-01 | Done
WORKPLACE EVALUATION BY HEALTH CENTER
| TM workplaces will be evaluated by Health center | Gansukh | 2015-11-01 | 2015-11-15
ENVIRONMENTAL MANAGEMENT SYSTEM
| Research of grey water removal | Tsogtbayar | 2015-06-01 | Done
| Get tested grey water by official lab |  | 2015-07-01 | Ongoing
| Comply the standard at grey water |  | 2015-08-01 | 2015-08-15
| Make a contract with the contractor to removed grey water at washers |  | 2015-08-16 | 2015-09-01
| Prepare database for setting the targets of Environment in 2016 |  | 2015-12-15 | 2015-12-20
UPDATE OHSE POLICY & PROCEDURE
| Contact with SMS OHSE Director | G | 2015-05-01 | Done
| Get approval on including Mongolian legislation into SMS Policy & Procedures |  | 2015-05-10 | Done
| Review the policy & procedures against Mongolian legislation |  | 2015-05-20 | Done
| Include the review policy & procedure to Company Induction |  | 2015-06-20 | Done
EMERGENCY RESPONSE
| Research Survival kit & First aid room's items | Tsend-Ayush | 2015-01-01 | Done
| Get approval on Survival kits & First aid room from Directors |  | 2015-02-02 | Done
| Build the kits |  | 2015-02-15 | Done
| Train all personnel |  | 2015-03-01 | Done
KPI in 2014 per 200.000 exposure hours
Lost Time Injury = 0
Total Recordable Injury Frequency < 0.6
Severity Rate < 15